## Slide 1: NEWPP Expansion Project Update
TTI Committee Briefing
April 16, 2018

## Slide 2: CONTENTS
1 | Project Background
2 | Project Advisor Role:
3 | Delivery ● Scope ● Cost
4 | Request for Council Actions

## Slide 3: Project Background

## Slide 4: Necessary for Subsidence Regulations & Growth
90
80
70
60
50
40
30
20
10
0
% of Water Demand Supplied by Surface Water
Current
January 2025
January 2035
Increase in requirement

## Slide 5: One Component of Regional Water Supply Plan
New Plant & Intake
(2024 Completion)
City/NHCRWA/CHCRWA TM
(2021 Completion)
Trinity
River
Lake
Houston
Luce Bayou Interbasin
Transfer (CWA Project)
(2019 completion)
WHCRWA/NFBWA TM
(2021 Completion)

## Slide 6: Project Partners
Cost Share
Chart: 
| North Harris County Regional Water Authority | West Harris County Regional Water Authority | North Fort Bend Water Authority | City of Houston | Central Harris County Regional Water Authority
 | 0.3531 | 0.2576 | 0.2141 | 0.16 | 0.0153

## Slide 7: Authority & City Consensus Required to Approve Amendments

## Slide 8: Role of the Project Advisor & Technical Consultant

## Slide 9: Project Stakeholders
9
Authority
Partners
Project Advisor
Public Works Teams
Permitting, Geotechnical, Finance, Transmission Mains, etc.
Legal Department
Design-Builder
Subcontractors
Subconsultants
Subconsultant
Team members
State/Federal Agencies
USACE, TCEQ, TWDB, etc.
City Contractual Relationship
HOUSTON PUBLIC WORKS
Notes: 9

## Slide 10: PATC Roles
Piloting and Process Confirmation
Staff Augmentation Through all Phases
Permitting Support
Procurement and Negotiation Support
Project Controls
Construction review & monitoring
Technical Collaboration & Review
In association with
5Engineering
Aviles Engineering
Capital Project Strategies
CP&Y
EJES Inc.
Gunda Corporation
Gupta & Associates
Hunt & Hunt Engineering
RPH Consulting Group
SES Horizon Consulting Eng
Strong Strategies, LLC
United Engineers

## Slide 11: PATC Provides Valuable Oversight
Validate each amendment to HWT’s contract, helping the Project partners save millions
Review all Project documents to make sure the City’s goals & requirements are met
Chart: Price (Million $)
| Amendments #2 & 3 - Component 2 Services | Amendment #4 - EWP #1 | Amendment #5 - EWP #4 | Amendment #6 - EWP #2 | TOTAL
Original HWT Proposal | 112 | 39.1 | 49.5 | 50.4 | 251
Guaranteed Maximum Price | 82.3 | 37.3 | 48 | 43.8 | 211.4

## Slide 12: City & PATC Project Progression Timeline

## Slide 13: Delivery ● Scope ● Cost

## Slide 14: Two-phase (progressive) Design-Build
Lessons learned from DBO delivery of original NEWPP
Owner involvement
Best opportunity to achieve an earlier completion milestone
Earlier cost knowledge
Better ability to adapt to market conditions
Reduces interface risk - “one throat to choke”
Houston
Designer/Builder
DBB
PDB
Houston
Designer
Contractor

## Slide 15: Progressive design-build (PDB) allows for ongoing scope and cost refinements
Preliminary Services
Final Design & Construction Services
Basis of Design
Contract Award & NTP
Final
Completion
Final Acceptance
late 2024
Price, Scope, Schedule
Contractually Agreed-to
Guaranteed Maximum
Price (GMP) late 2018
GMP
Proposal
Approval of
Amendments
Final Cost =
GMP + Approved Changes – Shared Savings Rebate
City & HWT jointly develop scope
HWT estimates costs
City independently validates costs
Scope refinements/ value engineering incorporated
GMP submitted & negotiated

## Slide 16: Progressive Design-Build allows ongoing scope and cost refinements
Preliminary Services
Final Design & Construction Services
Basis of Design
Contract Award & NTP
Final
Completion
Final Acceptance
late 2024
Price, Scope, Schedule
Contractually Agreed-to
Guaranteed Maximum
Price (GMP) late 2018
GMP
Proposal
Approval of
Amendments
Final Cost =
GMP + Approved Changes – Shared Savings Rebate
City & HWT jointly develop scope
HWT estimates costs
City independently validates costs
Scope refinements/ value engineering incorporated
GMP submitted & negotiated
Amendments:
Contract amendments are a planned part of the delivery
They are NOT change orders
They are used to authorize early work

## Slide 17: Preliminary budget based on Indicative Design prepared by PATC (Aug 2013)
PATC Estimated Design + Construction Cost: $1,167,000,000
Conventional WTP, no high-rating
NO ozone or chlorine dioxide
Belt press dewatering
Design-bid-build
On-shore raw water intake

## Slide 18: Conceptual campus layout per HWT Proposal (Oct 2015)
Estimated HWT Design-Build Cost: $893,000,000
Higher rate settling
(0.3 gpm/esf)
Higher rate filtration
(8.0 gpm/sf)
Single-story
Dewatering Bldg
(3 centrifuges)
Separate, single-story Admin & Maint Bldgs
Off-shore raw water intake
Ozone
Chlorine dioxide
NO recycle treatment
2 treatment modules

## Slide 19: Design enhancements help treat challenging raw water quality
Chart: Parameter Units (NTU, mg/L, PCU)
| 40995 | 40994 | 40991 | 40990 | 40989 | 40988 | 40987 | 40984 | 40983 | 40982 | 40981 | 40980 | 40977 | 40976 | 40975 | 40974 | 40973 | 40970 | 40969 | 40968 | 40967 | 40966 | 40963 | 40962 | 40961 | 40960 | 40959 | 40956 | 40955 | 40954 | 40953 | 40952 | 40949 | 40948 | 40947 | 40946 | 40945 | 40942 | 40941 | 40940 | 40939 | 40938 | 40935 | 40934 | 40933 | 40932 | 40931 | 40928 | 40927 | 40926 | 40925 | 40921 | 40920 | 40919 | 40918 | 40914 | 40913 | 40912 | 40911
Turbidity (NTU) | 27.5 | 31.9 | 31.6 | 23.6 | 26.9 | 30.9 | 30.8 | 35.6 | 39 | 43.7 | 39.3 | 44.9 | 49 | 47.2 | 48.2 | 51 | 44.4 | 46.3 | 44.6 | 43.8 | 43.8 | 47.2 | 47.6 | 44.5 | 51.9 | 35.4 | 37 | 38.4 | 39.4 | 42.1 | 43.5 | 40.5 | 48.5 | 43 | 49.7 | 40.1 | 42.7 | 40.3 | 45.2 | 45.7 | 31.7 | 33.2 | 29.4 | 29.2 | 26.3 | 28 | 28.5 | 25.2 | 25.5 | 24.9 | 22.4 | 18 | 18 | 15.5 | 16 | 16.3
Alkalinity (mg/L) | 34.7 | 35.6 | 32.7 | 28.6 | 30.3 | 32.5 | 31.8 | 32.18 | 36.3 | 37.7 | 33.5 | 28.7 | 30.1 | 30.1 | 29.6 | 29.1 | 31.1 | 28.5 | 28.6 | 30.2 | 30.6 | 29.5 | 29.7 | 28.4 | 37.1 | 31.7 | 32.4 | 33.1 | 32.7 | 31.9 | 34.4 | 34.1 | 32.6 | 36.5 | 38.3 | 49.7 | 46.3 | 52.3 | 51.03 | 46.9 | 62.98 | 62.95 | 71.8 | 69.3 | 75 | 68.3 | 70.4 | 79.6 | 74.45 | 78.4 | 86.3 | 92.9 | 92.9 | 97.9 | 95.5 | 95.1
TOC (mg/L) | 14.52 | 14.44 | 14.1 | 14.3 | 14 | 13.36 | 13.72 | 13.67 | 12.4 | 12.59 | 14.3 | 14.3 | 14.8 | 14.36 | 13.94 | 15.5 | 14.81 | 15.7 | 15.5 | 16.09 | 15.76 | 15.2 | 14.92 | 15.62 | 14.73 | 13.57 | 12.91 | 13.89 | 12.9 | 13.72 | 12.91 | 12.63 | 11.7 | 11.82 | 10.45 | 9.85 | 9.29 | 8.65 | 8.75 | 9.42 | 7.52 | 7.21 | 7.44 | 7.25 | 7.71 | 7.65 | 7.19 | 7.49 | 7.54 | 8.2 | 7.6 | 7.57 | 8.04 | 7.18
Color (PCU) | 32.2 | 31.8 | 32.2 | 31.2 | 31.2 | 30.3 | 31.1 | 31.5 | 30 | 29.5 | 32.7 | 36.6 | 40.34 | 39.2 | 36.2 | 36.9 | 37.9 | 39.1 | 37.4 | 38.46 | 38.38 | 38.5 | 38.08 | 38.59 | 35.2 | 31.1 | 30.13 | 31.15 | 31.16 | 30.9 | 30.02 | 29.8 | 28.4 | 27.2 | 23 | 23.8 | 21.4 | 21.9 | 24.3 | 15.4 | 16.9 | 13.3 | 14.7 | 12.9 | 14.4 | 14.2 | 11.3 | 11.9 | 11.37 | 8.76 | 7.41 | 7.41 | 7.43 | 7.1 | 7.65 | 6.88
Challenging raw water quality has led to previous plant shut-downs. New facilities are designed to prevent this from occurring in future.
Plant Shutdown
More ozone capacity helps oxidize high organics, color, & improve filtration
Lower filter and sedimentation rates help treat flashy water
Additional thickeners & centrifuges help handle more solids produced from storms
Chemical enhancements help handle drops in alkalinity

## Slide 20: HWT – Final BODR Addendum Estimate (June 2017)
Estimated HWT Design-Build Cost: $1,335,000,000
Multi-story
Dewatering Bldg
(5 centrifuges)
Lower rate filtration
(5.1 gpm/sf)
Off-shore raw water intake
Ozone
Chlorine dioxide
With recycle treatment
2 treatment modules
Reduced rate settling
(0.2 gpm/esf)
Single, Multi-story
Admin/Maint Bldg

## Slide 21: HWT – 30% Design Estimate (Jan 2018)
Estimated HWT Design-Build Cost: $1,684,000,000
Off-shore raw water intake
Ozone
Chlorine dioxide
With recycle treatment
2 treatment modules
Incorporates recent market data
Impacts larger site area (90 acres)
Reduced rate settling
(0.2 gpm/esf)
Lower rate filtration
(5.1 gpm/sf)
Multi-story
Dewatering Bldg
(5 centrifuges)
Larger
Single, Multi-story
Admin/Maint Bldg
More stormwater ponds

## Slide 22: Collaborative design process led to facility changes that increased cost estimates
 | Indicative Design Estimate | HWT Proposal Price | BODR Addendum Cost Estimate | 30% Design Cost Estimate
Estimated Non-oversized Cost | $1.167B | $893M | $1.335B | $1.684B
Incorporates Facility Enhancements* |  |  |  | 
Ability to operate intermittently at higher production (up to 425 mgd) |  |  |  | 
Traditional filter & pretreatment loading rates** |  |  |  | 
* Project elements added to increase reliability, redundancy, and robustness (e.g., additional dewatering centrifuges to handle large solids loadings during storm events). ** Reduced rates for settling and filtration at 320 MGD to account for challenging raw water quality events. |  |  |  | 

## Slide 23: Estimated costs changed in response to scope and market conditions
HWT
Proposal
Nov
30%
Design
Jan
$893
M
Apr
$1,684
M
Aug
June
Oct
June
Final BODR
Addendum
$1,335
M
2017
2015
2016
2018
Original Budget
Estimate
$1,167
M
Aug
2013
*Estimates are DB costs for HWT and do not include City administration, PATC, legal, and reserves.
$1,410
M
OVERSIZED ESTIMATES
NON-OVERSIZED ESTIMATES
$1,755
M

## Slide 24: Over-sized* facilities allow for future capacity increases
*Extra capacity beyond 320 MGD, paid for by City, but Authorities can elect
to participate by paying for costs proportional to their participation amount.
IPS: Larger building, extra pump cans
RW Pipelines:
2 @ 108” vs.
2 @ 96”
HSPS: Larger buildings, extra pump cans (x2 stations)
GST: Larger capacity
(x4 tanks)

## Slide 25: Filter Loading Rates Impact Cost
Chart: Estimated Quantities for Filter Modules 1 & 2
| Reinforcing Steel (tons) | Concrete (yards) | Buried Piping (linear feet) | Process Piping (linear feet)
Estimated Quantities HWT Conceptual Design | 2664.2565 | 21812 | 4120 | 3016
Estimated Quantities BODR Addendum | 4564.937 | 37175 | 6938 | 5200

## Slide 26: EWP Pricing Confirmed BODR Addendum Cost Estimates
*Some adjustments made to allow for comparison on a direct scope basis.
Chart: 
| EWP 1 | EWP 2 | EWP 4 | Total
Guaranteed Maximum Price | 37339594 | 43808897 | 39693728.632 | 120842219.632
Final BODR Addendum Cost Estimate | 31972753.38 | 40678093.114 | 45212000 | 117862846.494

## Slide 27: Final pricing based on competitively bid pkgs.

## Slide 28: Cost modeling summary
Project costs are estimates, NOT actual costs until a Guaranteed Maximum Price (GMP) is negotiated
Ability to adjust project scope relative to the budget
Opportunities to incorporate market-based information
Value engineering to reduce costs
Negotiations to adjust price
Under a traditional delivery, cost changes would not be known until bid day, with little ability to change

## Slide 29: Progress to Date

## Slide 30: Project is midway through the Preliminary Services phase
Preliminary Services
Final Design & Construction Services
Basis of Design
Contract Award & NTP
Component 1
Phase 2
(240 mgd)
milestone
Final
Completion
Final Acceptance
Transition & Warranty Services
Phase 1
(80 mgd)
milestone
6/30/22
(current estimate)
NEWPP Construction
Guaranteed Maximum Price Approval
GMP
Proposal
Early Work Packages
Component 2*
Amendments Approval
We are Here
* Design & pre-construction services
6/27/24
(current estimate)

## Slide 31: Design nearing 60% completion milestone

## Slide 32: EWP Construction Activities

## Slide 33: EWP Construction Activities

## Slide 34: 108-inch raw water pipe is ready for delivery

## Slide 35: MWBE Engagement Overview - Design

## Slide 36: MWSBE Participation – EWP Construction
Balance of Work
M/WBE Firms include Landtech, Fence Master, Lazer and Emerald
Balance of Work
M/WBE Firms include Rebar Reinforcement Placers, Cohen Industrial Supply, and C&B Waterworks, Inc.
Balance of Work
M/WBE Firms include Republic Traffic Safety, J. Simmons, Fierro Group, Z Logistics, M&D Foundation, AGS Consultants, All Steel
MWSBE Participation for
EWP 1 ($13.8M of $17.18M direct construction cost)
MWSBE Participation for
EWP 2 ($3.8M of $35.5M direct construction cost)
MWSBE Participation for
EWP 4 ($4.3M of $32.2M direct construction cost)
19.7%
80.3%
11.55%
88.45%
13.4%
86.6%

## Slide 37: Community Outreach
Website – greaterhoustonwater.com
Phone hotline – (281) 520-3777
Two public meetings held:
  October 25, 2017
  November 15, 2017
Construction notifications distributed
Upcoming public meeting (May 1)
Weekly coordination meetings – construction & outreach teams
Over 70 contractor outreach events between February 2017 & April 2018, including:
  National Association of Minority Contractors
  PWE Contracts in 5
  Greater Houston Black Chamber of Commerce
  Greater Houston Business Procurement Forum
  Women Contractor’s Association
  Houston Contractor’s Association

## Slide 38: Requests for Council Action

## Slide 39: Upcoming Requests for Council Action
Action | Approx. Date | Amount
Approve HWT Amendment 6 – EWP #2A | April 2018 | $45.5M
Approve HWT Amendment 7 – EWP #5 | Spring 2018 | TBD
Approve HWT Amendment 8 – EWP #6 | Summer 2018 | TBD
Approve HWT Amendment 9 – EWP #7 (tentative) | Summer 2018 | TBD
Approve HWT Amendment – GMP for Balance of Plant | Late 2018 | TBD
Approve PATC Amendment | Mid-Late 2018 | TBD

## Slide 40: NEWPP Expansion Project Update
TTI Committee Briefing
April 16, 2018